## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Guest Ordering API | 8 |  | 19 | 7.5 | 6 | 11 | 1 | 1 | 0 | To Do
Define Model for Guest Order |  | Atong | 7 | 5 | 3 | 0 | 0 | 0 | 0 | Done | 0
Create basic API for placing orders |  | Atong | 8 | 1 | 1 | 5 | 0 | 1 | 0 | Done | 0
Implement basic validation for order items |  | Atong | 1 | 0.5 | 0 | 3 | 0 | 0 | 0 | Done | 0
Complete basic tests for order |  | Atong | 3 | 1 | 2 | 3 | 1 | 0 | 0 | Done | 0
Menu API | 13 |  | 19 | 15 | 19.5 | 6.5 | 3 | 1 | 0 | To Do
Define basic data for menu orders |  | Thomas | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 2
Create basic API for retrieving menu items |  | Thomas | 3 | 5 | 5 | 1 | 1 | 1 | 0 | Done | 0
Add basic filtering for category |  | Thomas | 8 | 2 | 5 | 0 | 1 | 0 | 0 | Done | 1
Complete basic test for menu retrivial API |  | Thomas | 5 | 5 | 9 | 5 | 1 | 0 | 0 | Done | 1
Order Status API | 5 |  | 19.5 | 8.5 | 3.5 | 3.5 | 4 | 1 | 0 | To Do
Create API for checking order status |  | Atong | 8 | 6 | 0 | 0 | 0 | 0 | 0 | Done | 0
Implement order status flow (placed, preparing, completed, etc) |  | Atong | 8 | 1 | 3 | 3 | 3 | 0 | 0 | Done | 0
Complete basic test for order status retrivial |  | Atong | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | Done | 0
Complete test for order status updates |  | Atong | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | Done | 3
Payment API | 8 |  | 25.5 | 12.5 | 13.5 | 13.5 | 5 | 2 | 0 | To Do
Create basic API for payment processing |  | Thomas | 9 | 4 | 2 | 2 | 1 | 1 | 0 | Done | 0
Create mock payment system |  | Thomas | 6 | 6 | 3 | 3 | 3 | 1 | 0 | Done | 1
Implement basic payment status |  | Thomas | 6 | 2 | 8 | 8 | 1 | 0 | 0 | Done | 1
Complete basic test for Payment API |  | Thomas | 4.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 0
User Authentication API | 3 |  | 17 | 16.5 | 16.5 | 6.5 | 7 | 13 | 0 | To Do
implement user registration |  | Atong | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 1
Implement user login |  | Atong | 6 | 6 | 6 | 0.5 | 3 | 9 | 0 | Done | 0
Generate basic auth. token |  | Thomas | 7 | 9 | 9 | 4 | 3 | 3 | 0 | Done | 3
Complete basic test for user auth. |  | Thomas | 2 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0 | Done | 1
TOTAL |  |  | 100 | 60 | 59 | 41 | 20 | 18 | 0 |  | 14